## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 22 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
[6 empty] | Week1 |  |  |  |  | Week2 |  |  |  |  | Week3 |  |  |  |  | Week4 |  |  |  |  | Week5 |  |  |  |  | Week6 |  |  |  |  | Week 7
Experimentation Plan | 4 | 7 | 4 | 7 | 100%
MIMO->SISO | 7 | 6 | 7 | 6 | 100%
Camera Detection | 9 | 11 | 9 | 11 | 40%
Modelling: Analytical EoM | 9 | 11 | 9 | 11 | 40%
Modelling: Linearised EoM | 14 | 6
Simulink: Logger | 14 | 6
Simulink: Stateflow Logic | 14 | 11
Controller: Feedforward Design | 12 | 13
Controller: Feedback Design | 9 | 16
Controller: Final Tests & Improvements | 24 | 9
A4 Poster | 24 | 8
Promotional Video | 24 | 8
Project Discussion | 27 | 9